## Release Details of IVTECH-IVTEC
Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM
Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM | Release Details of IVTECH-IVTECH as on 23-Jul-2025 06:39:04 PM
Application | Version | DEV | QA | UAT | LIVE | Description
All | 1.0.3 | 16-Jul-2025 | 21-Jul-2025 | 25-Jul-2025 | 31-Jul-2025 | Development of features and functionalities associated in Milestone 5
All | 1.0.2 | 13-Jun-2025 | 20-Jun-2025 | 21-Jul-2025 | 31-Jul-2025 | Development of features and functionalities associated in Milestone 4
All | 1.0.1 | 24-Apr-2025 | 30-Apr-2025 | 21-Jul-2025 | 31-Jul-2025 | Development of features and functionalities associated in Milestone 3
All | 1.0.0 | 17-Mar-2025 | 18-Mar-2025 | 20-Mar-2025 | 31-Mar-2025 | Milestone 2: SRS for License & BI Dashboard Web Applications