## IVTECH
Sr.No | Checkpoints | Comments | Remark
1 * | Is Project kick off meeting conducted & MOM created and uploaded on central repository? | Yes | Click Here to open it
2 * | Is latest signed Project proposal/Contract prepared for particular duration & uploaded on Spectrum? | Yes | Click Here to open it
3 * | Is Project SOW prepared or available in SPECTRUM? | Yes | Click Here to open it
4 * | Is time sheet filled by all assigned members of the project in SPECTRUM? | Yes
5 * | Is meaningful task bifurcation done and assigned to resources? | Yes | Click here to open example
6 * | Is task status updated on regular basis? | Yes | Click here to open it
7 * | Is Software development plan document created with proper revision history, naming convention & placed on central repository? | Yes | Click here to open it
8 * | Is Project/Release schedule created and uploaded on central repository? | Yes | Click here to open it
9 * | Are the project specific tailoring needs identified and approved for deviation if any? | - The roles of Project Manager and UI/UX Designer were excluded from the project scope. This deviation was reviewed and approved by our CEO. - SPEC QA activities were also excluded, as the client opted to perform testing using their own camera setups. This was agreed upon and documented during project discussions.
10 * | Is Risk list created and uploaded on central repository? | Yes | Click here to open it
11 * | Is Customer property form filled up and uploaded on central repository ? | Yes | Click here to open it
12 * | Is MOM or emails for status update with client uploaded on central repository? | Yes | Click here to open it
13 * | Is SRS created with all formal requirements with proper naming convention & uploaded on central repository? | Yes | Click here to open it
14* | Is SRS reviewed and approved by client? | Yes | Click here to open it
15 * | Is CR created in SPECTRUM/RED and assigned to respective verticals? | NA
16 * | Is SAS document created with proper naming convention & uploaded on central repository? | Yes | Click here to open it
17* | Is Impact Analysis document created for CR & uploaded on central repository proper folder structure? | NA
18 * | Is Impact analysis document shared and approved from client? | NA
19 * | Has the code review being done and findings logged in SPECTRUM? | Yes | Click here to open example ticket
20 * | Is Unit testing done & issues reported in SPECTRUM? | Yes | Click here to open example ticket
21 * | Are Test cases created & reviewed for Release/Project? | NA | SPEC QA is not involved in this project
22 * | Are all release documents (test plan, release note, CGR, IG, Release checklist) created with proper naming convention & uploaded on central repository? | NA | SPEC QA is not involved in this project
23 * | Is Test Report created, approved & uploaded on central repository with proper naming convention ? | NA | SPEC QA is not involved in this project
24 * | Is Test case execution details recorded? | NA | SPEC QA is not involved in this project
27 * | Is UAT sign off doc created & signed by client? | NA | At present, development for the project is in-progress
28 | Is Customer feedback form filled during Project Closure? | At present, development for the project is in-progress | Click here to open it
29 * | Is root cause analysis done in case of effort variance? What action is taken for such cases? | Yes